APA CALIFORNIA BOARD

CONFERENCE REQUIREMENTS HANDBOOK

Last UpdatedDecember 2009

The following are requirements that each Conference must include as part of their conference planning.  This document outlines what the APA California Board of Directors expects of the Conference and the Conference Committee.  Areas not covered in this handbook are at the discretion of the VP of Conferences.

Table of Contents

INFO BY TIMELINE:

CONFERENCE MANUAL TIMING ROADMAP

INFO BY SUBJECT:

#### I.	Getting Started	4

A.   Review & Incorporate APA California Conference goals …………………..….……….4

B.   Establish Site Selection Committee 	5

C.   Establish Conference Steering Committee 	5

1.  Select Conference Co-Chairs 	6

2.  Recruit and Select Committee Chairs	6

D.   Mandated Section Director Board Liaison & Other Chairs 	6

E.   Recommended Chairs and Committees ………..……………………………………..…7

II.	Consultants and Contracts

A.   Mandatory Use of Conference Consultants	8

B.   Other Contract Review by APA California Attorney	8

#### III.	Establishing the Conference Budget	9

A.   Conference Committee Develops Budget	9

B.   Conference Expenses	9

C.   Board Approval of Conference Budget	9

D.   Conference Loan	9

E.   Conference Profits	10

F.   Conference Profit Distribution	10

G.  Conference Losses	10

H.  1099 Tax Forms from Vendors	10

I.    Additional Budget Considerations	10

1.  Complimentary Registrations	10

2.  Complimentary Hotel Rooms	12

3.  Registration Fees	12

IV.	Insurance and Risk Management	14

A.   Catastrophic Insurance	14

B.   Use of Chapter Liability Insurance	14

C.   Conference Activities Approved by APA California Attorney	14

D.   Association and Section Activity Guidelines	14

V.	Planning the Program	15

A.   Identifying a Theme	15

B.   Conference Program	15

C.   Guidelines for Session Submittals	15

D.   Mandatory Board Program Sessions & Liaison	17

E.   Mandatory Special Events	18

1.  Awards Ceremony	18

2.  CPF Fundraiser and Auction	19

3.  Student Conference & Student Awards Lunch	19

F.   Required Meeting Rooms for Leadership Meetings	19

G.   Certification Maintenance Credit	20

1.  Putting out the Call for Sessions	20

2.  Before the Conference	20

3.  During the Conference	21

4.  After the Conference	21

VI.	Advertising the Conference	23

A.   Cal Planner	 ………………………………………………………..23

B.   Section Newsletter	23

C.   APA California Website – Conference Posting Process	23

D.   Conference Website	24

E.   E-Mails Directly to APA California Members	24

#### VII.	Exhibit Booths/Display Space	25

A.   Complimentary & Contracted Display Space	25

#### VIII.	Miscellaneous Items	26

A.   ADA Compliance & Notice in Registration Materials	26

B.   Reserve Hotel Rooms for APA California Board	26

C.   Extra Hotel Rooms	26

D.   Registration Confirmation	26

#### IX.	At the Conference	27

A.   Thank the Conference Committee	27

B.   Head Table for APA California Board	27

C.   APA California Board Registration Packet Distribution	27

D.   Ribbons for Name Badges for Leadership and Speaker Identification	27

X.	Standing Conference Committee	28

#### XI.	Updating the Conference Handbook	29

Appendices	30

A.   APA California and Section Legal and Insurance Activity Guidelines	31

B.   Conference Coordinator Responsibilities	37

C.   Conference Account Management Consultant Repsonsibilites and Conference Financial Requirments

- Management Conference Responsibility

- Financial Policies

- Conference Accounting Procedures

- Conference expense and Reimbursement Claim Form

- Registration Company Check Payment Breakdown Form

- APA California Conference Check  or Vendor Payment Request Form

D.   Sample Conference Budget	48

E.   Conference Design and Publication Management Consultant	49

F.   Recommended Committee Structure/Roles and Responsibilities 	50

G.   Conference Themes	51

H.     Evaluation Form for CM Sessions

60

NOTE:  SUBJECT ITEMS AND PAGE NUMBERS SHOULD BE CHECKED FOR ACCURACY WHEN DRAFT IS FINALIZED.

OUTSTANDING ITEMS:

- (	Provide format for conference closure report C., page 8.   (Hing)

- (	Revise Conference Rates for APA Life Members to be consistent with National

policy, p. 13, 3. (Collette)

- (	Update Continuing Ed section and draft Member Credit Request Form (Carol), G., Page 20.

- (	Get Cal State Northridge contact info for display space, page 24.

I.	GETTING STARTED

The APA California Conference is held every year in the fall, in the months of September, October, or November.  The Conference generally commences on Sunday, with a Student Conference and student awards luncheon Sunday afternoon and an opening reception on Sunday evening, and ends on Wednesday mid-day.

The critical first steps include the review of the Conference Goals below, and formation of a site selection committee and host committee.  The committees can be two separate committees or one, whatever the Host Section prefers to do.

A.	REVIEW AND INCORPORATE APA CALIFORNIA CONFERENCE 	GOALS

It is important to keep in mind the purpose of the Conference at the beginning stages of the Conference, through the planning of the Conference, up to the date of the Conference itself.  Therefore the Board has adopted the overall Goals listed below that shall govern decision making by the VP of Conferences and Host Committee.

The Conference shall:

- Provide continuing education for members.

- Provide AICP CM credits for all sessions and workshops.

- Provide networking opportunities.

- Provide dynamic, motivational, current and topical keynote speakers.

- Provide an atmosphere that is of high quality in all aspects of the Conference,     including:

  - Conference Venue and Hotel

  - Opening Reception, Other Special Events and their Locations

  - Meals

  - Sessions

  - Mobile Workshops

  - Keynote Speakers.

- Achieve the conference profit specified in E. on page 11.  Profits anticipated above the profit specified in E. should be redirected by the host Section to increase the quality, and/or reduce the price to members, of the Conference and of Items 1-4 above.

B.  Establish Site Selection Committee

Primary Responsibility:  The primary responsibility of the Site Selection Committee is to scout out potential city and hotel/conference locations within the Host Section with the APA California Conference Coordinator. The committee shall consist of the VP of Conferences and the President Elect, Past President and the Section Director from the region being considered.

The Site Selection Committee must investigate alternative city/county sites and hotels and provide to the APA California Board information concerning at least two or three city/county and hotel alternatives along with the Site Selection Committee’s recommendation for the site they prefer. T

Given the APA California goal of moving the conference around the State to each of the eight sections, it is also important to identify locations different than the last location the Section hosted the conference.

Time Frame:  The Site Selection Committee should be formed a minimum of 36 months  prior to the estimated conference date.  Given the growing size of the state conferences over the past decade, it may be prudent to form the Site Selection Committee three years prior to the estimated conference date to allow the Committee time to find an adequate number of sites that meet the APA California requirements.

Factors to Consider in Site, Hotel and Date Selection:  The Site Selection Committee shall attempt to select hotels that employ union employees and that are not the subject of a strike.  The conference hotel(s) must be ADA accessible.  In selecting the date for the conference, the Conference Committee must avoid conflicts with religious holidays and other conferences, including but not limited to the League of California Cities and County Supervisors Association of California (CSAC) conferences, and the National APA Fall Leadership Meetings.

Board Approval for Site, Hotel, and Date:  The APA California Board shall approve the conference site (city/county and hotel) at a Board meeting or by e-mail Board vote.  Selection of the city/county and hotel must be made at least two years prior to the conference.

The APA California Board shall also approve the date selection at the same time as the site selection, and will review the conference profit amount each year at the time of the selection of the venue to ensure that the conference profit amount keeps up with inflation and Chapter financial needs.

C.	Establish Conference Host Committee

A cohesive, well-organized, and unified Conference Host Committee will make all the difference as the host committee spends approximately two years planning the conference.

The Host Section should utilize the Section’s website and newsletter to announce the formation of the Committee and the wealth of opportunities that exist for members to get involved in the preparation of the conference, including but not limited to assisting with mobile workshops, opening reception, volunteers and a portion of the programs/sessions.

- Select Conference Host Co-Chairs

Co-Chair Requirements:  The Conference Host Committee should appoint at least two co-chairs.  The goal is to have equal representation from both the public and private sectors, and ideally to have one co-chair from each sector.  However, it is more important to have capable co-chairs that have proven leadership skills.

Board Approval for Co-Chairs:  The Host Section shall forward the names of the Co-Chair recommendations to the APA California Board for ratification.  The recommendation shall include the individuals’ APA and professional experience.

2.	Recruit and Select Committee Chairs

The next step is for the Co-Chairs to select the Committee Chairs.  It truly takes a community of local professional planners to organize, plan, and host a successful State Conference.  The mandated and recommended roles and responsibilities of the committees identified in this section are outlined below and in Appendix F. (THIS NEEDS REVISING)

Recommended Host Committee Members/Chairs:

Facilities Committee

Mobile Workshops Committee

Programs Committee and 2-3 appointees to state Programs Committee

Opening Reception Committee

Local Sponsorship Committee – is the state sponsorship position coordinated with this position?

Volunteer Committee

The VP of Conferences will coordinate with the Host Section Director to ensure formation of host committee chairs.

D.  Mandated Section Director/APA California 	Board Conference Liaison and Other Mandated 	Committee Chairs

- Section Director as Board Liaison

Duties:  The Director of the Host Section will serve as liaison between the Conference Committee and the APA California Board and affiliated groups unless another Board member from the Host Section is specifically designated to serve as liaison.

Reports to Board:  The Chapter VP of Conferences will provide a conference update to the APA California Board at each Board meeting beginning one year prior to the conference date.

The Section Director will also provide monthly updates to the VP of Conferences who will communicate with the Board.  The update consists of completing the Conference Timing Roadmap and checklist at the front of the manual. Preparation Checklist (see Appendix B) by the end of the each month and submitting the most recent checklist to the APA California Board by e-mail as an attachment for the Board meetings as they occur.

The Section Director shall also forward Conference Host Committee minutes to the VP of Conferences who will forward them to the APA California Board by e-mail if warranted?

Conference Closure Report to Board:  The VP of Conferences and the Host Section Director shall provide the APA California Board with a Conference Closure Report at the January/February APA California Board meeting following the conference.  The Conference Closure Report shall include: (HING TO PROVIDE FORMAT FOR CONFERENCE CLOSURE REPORT)

- VP of Public Information

a.	Public Relations/Press Coordinator

Duties: The Chapter VP of Public Information shall be in charge of coordinating any press attending the conference.  The Conference Press Coordinator shall work with the APA California Public Relations Director/consultant so that the Conference Host Committee is aware of press invited and expected to attend the conference.  The VP of Public Information will also greet press attending the conference, prepare and provide them with session information, and guide them to the sessions or events they wish or were asked to attend.

b.	Web Site Chair

Duties:  The Chapter VP of Public Information/Technology Director in coordination with the Conference Coordinator Consultant shall have the overall responsibility to ensure that the Conference site on the Chpater’s website is updated and populated and shall be authorized to update the Conference website.  However, any changes to the APA California Website or articles/announcements that will be featured on the APA California website homepage or other areas of the website  shall be completed by the APA California management firm.

- Recommended Host Committee Members/Chairs:

Facilities Committee, Mobile Workshops Committee, Programs Committee, Opening Reception Committee, Local Sponsorship Committee, Volunteer Committee, the Chapter VP of Conferences coordinates with the Host Section Director to ensure formation of host committee chairs.

Action Items for the section:

Action Item

Review and Incorporate APA California Conference Goals

Action Item

Form Site Selection Committee 36 Months Out

Action Item

Seek APA California Board Approval of City/County, Hotel, and Date 36 Months Out

Action Item

Establish Conference Host Committee 18 Months Out

Action Item

Select Conference Host Co-Chairs

Action Item

Seek APA California Board Approval of Conference Host Co-Chairs

Action Item

Co-Chairs Select Committee Chairs

Action Item Host Section Director Reports to Board at Each Board Meeting 12 months Out

Action Item

Host Section Director Provides Monthly Updates and Minutes to VP of Conferences who will communicate with Board

Mandatory Use of Consultants

Acton Item

Contact Contractors to Work out Schedule of Work and Timelines

Action Item

Have all Other Conference Contracts Reviewed by APA California Attorney

II.	CONSULTANTS AND CONTRACTS

A.	MANDATORY USE OF CONFERENCE Consultants

As the size of the conferences has grown over the last decade, the APA California Board has determined the need to have consistency year to year and consistency between providers.  As a result, the APA California Board now requires every conference committee to use the same Board-contracted providers, identified below:

1.	Conference Coordinator Consultant

2.	Conference Registration and On-Site Registration Consultant

3.	Accounting Management Consultant

4.	Design/Graphics/Publication Consultant

5.	PR Consultant

6.	Web Consultant

7.	Insurance Provider:  (The Conference Committee is	required to coordinate for insurance through the APA California Board Director of 	Administration to ensure that the conference has the appropriate insurance coverage.  The Director of Administration will then contact the insurance provider.)

The APA California Board reserves the right to change consultants at any time.  All contracts with the consultants will be approved by the APA California Board and signed by the APA California President and the APA California attorney as to form.

The names and contact information for each contracted consultant, their roles and responsibilities, and their relationships with both the conference committee and the APA California Board are articulated in Appendix C.

- CONFERENCE Contract Review by APA CALIFORNIA Attorney

All contracts for the conference other than those listed above, that are arranged by the VP of Conferences, including those with facilities, transportation providers, and paid speakers shall be reviewed by the APA California attorney Marco Martinez with Best, Best & Krieger LLP (949-263-2600, marco.martinez@bbklaw.com) to ensure that indemnification and insurance clauses adequately protect APA California and the conference.

III.  	ESTABLISHING THE CONFERENCE BUDGET

A.	VP of Conferences and VP of ADMINSITRATION Develops Budget

The VP of Conferences in consultation with the VP of Administration shall develop a preliminary conference budget.  As noted below, all conference expenses shall be accounted for in the budget.  The budget shall detail anticipated revenues from registration fees, exhibitors, sponsorships, and any other revenue sources.  In addition, all anticipated expenses shall be detailed, including administration costs, special event costs, transportation, meals, vendors, publicity, reproduction, website, registration, repayment of the Chapter advance and any other expenses.  A sample budget is provided in Appendix D.

B.	Registration Fees

The amount of the registration fees shall be included in the budget and approved by the Board with the budget approval. (See I. 3 – Registration fees for information on setting the fees.)

c.  Conference Expenses (also Financial Policy)

All conference expenses will be included as part of the conference budget, and will not be included as line items in the APA California budget, including Board contracted services.  Exceptions include those expenses directly related to the APA California Board meeting held during the conference.  The conference committee shall contact Stefan/George Associates to determine the Board contracted line item expenses.

d.	Board Approval of Conference Budget

The APA California Board shall review the preliminary conference budget for comment, and shall approve the final budget and profit estimate pursuant to E.  The budget approval shall be completed at a Board meeting or by e-mail Board vote.  The approved conference budget will then be used by the Accounting Management Consultant to set up the conference financial reports and accounts.

E.  Conference BANK ACCOUNTS AND INITIAL CONFERENCE COMMITTEE advance (also Financial Policy)

Stefan/George Associates will maintain for the Chapter two conference checking accounts at all times. One will be used as the current conference account accounts for the current conference, and the other for the conference for the following year.  Each account shall maintain a minimum balance of $15,000 that can be used as an advance by the conference committees to cover initial conference expenses.

E.	Conference Profits (also Financial Policy)

The annual conference is a major revenue source for APA California and the eight Sections.  A profit of at least $100,000 should be achieved.  The Board will review the conference profit amount each year at the time of the selection of the venue to ensure that the amount keeps up with inflation and Chapter financial needs.

Any amount of the $15,000 advance used by the conference host committees shall be considered a conference expense and shall be paid back to the Chapter from conference profits.

- CONFERENCE PROFIT DISTRIBUTION (ALSO FINANCIAL POLICY)

To be revised at the retreat

Before any profits are distributed to the Chapter, the Accounting Management Consultant will pay all conference expenses from gross conference revenues, including the $15,000 loan to the Host Section, costs of accommodations and other bills associated with the conference, and the cost of all Board-contracted professional consultants.  Following payment of conference expenses, the Accounting Management Consultant will disburse the net conference profits using the following formula:

| Recipient | Percentage |
| --- | --- |
| APA CA | 40% |
| HOST SECTION | 40% |
| ALL OTHER SECTIONS | 20% |
| TOTAL | 100% |

G.	Conference Losses

In the event a conference loses money, the Board, at the next Board meeting or by phone/fax vote, will determine how debts are to be paid.

H.	1099 Tax Forms From Vendors

Any 1099 tax forms sent to the Conference Host Committee by vendors shall be sent to the Accounting Management Consultant.

I.	Additional Budget Considerations

- Complimentary Registrations

APA CA Award Winners

All APA California award winners will be provided with one free admission to the awards ceremony and one meal.  Additional meals or one-day registration to sessions shall be available for purchase separately.

CPF Student Award Winners

The four top winners of the CPF scholarship awards receive a free full student registration for the conference.  The remaining CPF scholarship award winners will be provided one free admission to the student awards ceremony on the Sunday before the conference and meal at the student awards ceremony.  The CPF Board conference liaison shall contact the VP of Conferences to relay information about the CPF award winners.

## Speaker Payment and Registration Fees

Except for professionals engaged as keynote speakers, conference speakers are not paid.

Action: Conference Speaker Fees

The Committee decided to set up a new speaker conference registration fee.  Non-APA members who register as a speaker will not be charged the conference registration fee, if they are not otherwise attending the conference.  APA members who register as a speaker will receive a 20% discount off of the registration fee, for either the one-day or full conference registration rate.  The Vice President, Conferences will have discretion to grant a fee waiver if a speaker is unable to pay the fee.  Such waiver requests will be sent directly to the VP, Conferences.

Press

Press attending the conference will be provided with a complimentary Press Pass to cover the, but will be required to pay for their hotel expenses and any meals.  The number of press that will be provided complimentary Press Passes must be approved in advance by the Vice President for Public Information, and the VP of Conferences.  The VP of Public Information shall work with the PR Consultant so that the Conference Host Committee is aware of press invited and expected to attend the conference, and to ensure the press are greeted, provided session information, and guided to the sessions or events they wish or were asked to attend.

APA California President

Full conference registration shall be provided for the APA California President.

APA California VP of Conferences

Full conference registration shall be provided for the APA California VP of Conferences.

APA California Staff/Consultants

Full conference registration shall be provided for the following APA California staff/consultants:

- APA California Executive Director

- APA California Administrative Director

- APA California Conference Coordinator Consultant

- APA California PR Consultant

- APA California Registration Consultant

- APA California Attorney

Invited Guests of Invited Guests of APA California President

The APA California President may invite four guests from other chapters or from National APA.  These guests will receive free registrations for the basic conference.  If they attend any optional events or mobile workshops, the guests will be responsible for paying for these themselves.

Region VI Board Representative and AICP Commissioner

Full conference registration shall be provided for the National APA Region VI Board representative and AICP Commissioner.

- Complimentary Hotel Rooms

Complimentary hotel rooms in the main conference hotel shall be provided by the Conference Consultant for the length of the conference to the following:

- One presidential or hospitality suite for the APA California President

- One room for the Executive and Administrative Directors

- One room for APA California Conference Coordinator Consultant

- One room for APA California Public Relations Consultant, but only upon the request of the Vice President, Public Information for the days the VP designates.

- One room (up to four) each for invited guests of APA California President (could include National APA Executive Director, National APA President or others determined by APA California President)

- One room for Region VI Board representative

- One room for Region VI AICP Commissioner

- One room for the VP of Conferences

- Registration Fees

Minimum Registration Rates

Conference registration rates shall be set to ensure all conference costs and profit requirements are met. The fee will vary based on site location and costs and will be approved by the Board with the approval of the conference budget.

Reduced Conference Rates for Students

Reduced rates will be provided to students at all APA California-sponsored conferences.  The APA California Chapter Board shall decide the amount of the reduction, but the reduced fee at a minimum shall cover food and beverage costs.

Reduced Conference Rates for APA Life Members

Reduced rates will be provided to Life APA members (APA members are eligible for Life Membership after 25 years or more of continuous membership).  The APA California Chapter Board shall decide the amount of the reduction, but the reduced fee at a minimum shall cover food and beverage costs.  [This fee needs to be consistent with National APA policy]

COLLETTE TO PROVIDE THIS INFORMATION – AWAITING INFO FROM DEENE ALONGI

Non-Member Membership Registration Option

Registration materials shall provide an option for non-members to sign up as members when they register for the conference.

Action Items for the section:

Action Item

Develop Conference Budget

Action Item

Board Approval of Conference Budget

Action Item

Review and Meet Conference Profit Requirements

Action Item

Review Conference Profit Distribution

Action Item

Send Any 1099 Tax Forms to Stefan/George Associates

Action Item

Provide Complimentary Registrations

Action Item

Contact the Director of Administration to Obtain Required Insurance and Adhere to Section Activity Guidelines in Appendix A

IV. INSURANCE AND RISK MANAGEMENT

A.	Catastrophic Insurance

The VP of Administration must obtain catastrophic/conference interruption insurance for the conference to ensure the conference profits are not jeopardized by a disaster such as earthquake or flood.  The VP of Conferences shall contact the Director of Administration to obtain the insurance from the APA California insurance provider.

B.	Use of Chapter Liability Insurance

Chapter liability insurance covers the conference; however, off-site activities and use of outside vendors or companies are not covered by this insurance.  For information about the Chapter liability insurance, or for proof of insurance required by the conference venue, contact the Director of Administration. The conference must require that transportation companies for mobile workshops or other conference-related events carry their own insurance.

C.	Conference Activities to be Approved by APA CALIFORNIA Attorney

To ensure that APA California and the Conference Host Committee are not taking inappropriate risks, activities other than those already specified on the APA California liability insurance policy must be reviewed and agreed to by the APA California insurance provider and the APA California attorney.  These activities shall be outlined by the Conference Committee to the APA California Director of Administration as early as possible in the planning process so that the Director can contact the insurance provider for approval.  All additional insurance contracted for by the Conference Host Committee shall be obtained through the Director of Administration and the APA California Insurance Provider and referred to the APA California attorney for review.

- Association and Section Activity Guidelines

The Conference Host Committee shall also adhere to the legal guidance concerning insurance and activities in the insurance policy listed coverage and the attached Association and Section Activity Guidelines (see Appendix A).

E. Disability Inquiries and Complaints

The VP of Conferences and the conference management firm shall be the points of contact for the disability inquiries and complaints concerning the conference and conference facilities.

Any Injuries or complaints shall be forwarded to the APA CA attorney before responses are provided.

V.	  PLANNING THE PROGRAM

a.	Identifying a Theme

The local host committee shall propose a conference theme and logo for the APA California Board to approve 9 months prior to the conference..  The APA California Board reserves the right to require the theme to highlight an issue of importance to the Chapter.  The theme approval shall be completed at a Board meeting or by e-mail Board vote

b.	Conference Program

The APA California Board shall approve the final draft program, and reserves the right to reschedule sessions to avoid double booking key Board members, or eliminate duplicative sessions.  The program approval shall be completed at a Board meeting or by e-mail Board vote 8 months prior to the conference.

c.	Guidelines for Session Submittals

The Chapter VP of Professional Development in conjunction with the Chapter Conference Programs Coordinator must contact the Design/ Graphics/Publications Consultant as soon as the Programs Coordinator  is appointed to develop the conference publication schedule.  In addition, the Chapter Programs Coordinator shall review the following Guidelines for sessions:

- The Call for Presentations should occur approximately 9 months prior to the date of the conference, including posting on the APA website.

- All submittals should be done electronically through a link on the state website.

- All abstracts should be limited to a specific word/character count, approximately 100-150 words or 1000- 1250 characters.

- All session abstracts should be limited to a maximum of 4 presenters per session.  Too many speakers in one session will be distracting and make it difficult to complete the session.

- Reminder e-mails should go out for the Call for Presentations at least three times:  when the first official Call for Presentations is announced, 1 month before the Call for Presentations deadline, and 1 week before that deadline.  The e-mail list used should be the most up-to-date member e-mail list from National.

- If the Chapters Programs Coordinator does not receive an adequate number of presentations, the Committee should send out an e-mail that extends the deadline for two weeks.

- The Chapter Program Coordinator should allow a minimum of two months to sort through abstracts, and review, rate and rank them.

- The Chapter Program Coordinator shall establish a conference program committee that will work with the host section to include 20% of the sessions to show case the host section and host region. Need to incorporate action item below:

Action: Conference Program Selection Process

The Committee decided to amend the draft Conference Handbook suggestions for Conference program session selection as follows:

- The Sections will automatically be given the choice of 20% of the conference programs.

- In addition, 2 to 3 members of the section session selection committee, rather than one, will be members of the state Chapter host session selection committee.

- The final session selections will be completed through a collaborative process between the state and sections.

- The host section will be able to suggest additional programs to the state Chapter session selection committee and will create the Call for Presentations, conference graphics, and determine the mobile workshops and the program tracks.

- Sections that in the future will be unable to host the state conference will also have the ability to suggest sessions to the state Chapter session selection committee.

- Then the Chapter Program Coordinator should contact those people whose abstracts were selected, identifying who the chosen session moderator should contact for questions and equipment needs, and providing deadlines and information that the Program Committee will need to finalize the program.

- The Statewide Program Coordinator should also notify those whose abstracts were not selected, thanking them for their submittal.

- Remember to remind all speakers that they must register for the conference.  Work with the Conference coordinator on a speaker’s registration code if the speaker is only coming for one day.  A separate speaker’s registration page might be helpful.  The Conference Registration Consultant can make a speakers’ only page for speaker registration.

- Final Abstracts with times and rooms, in the order they are going into the conference booklet, must be submitted to the Design/Graphics/Publication Consultant no later than 2 months prior to the conference.

- The Conference Program Committee? committee can decide how to handle the speaker bios.  The bios can be placed at the end of each session in the conference schedule in the conference booklet, at the end of the conference booklet in alphabetical order, or not included in the booklet, but placed on the website.  Speaker Bios take up approximately 40-50 pages of the booklet.

- Session Tracks should be reflective of the theme of the conference.

- Keep the session tracks simple.  Remember, the sessions should also reflect all types of planning.  We have urban, suburban, and rural areas in the state.  The Program Committee should also use the programs to showcase the local region.

- One track should be set aside for Planning Basics/Professional Development, including a CEQA/Environment training session.

- Sessions should be 1 hour 15 minutes to 1 hour 30 minutes each.

- The Chapter Program Coordinator might reserve the first session block as a “Super Session” area: areas deemed of critical importance or super topics that are hot at the moment.  These sessions should be a minimum of 1 hr 30 minutes.

- The Chapter Program Coordinator might reserve the first session block as a “Super Session” area: areas deemed of critical importance or super topics that are hot at the moment.  These sessions should be a minimum of 1 hr 30 minutes.

- The Chapter Program Coordinator may wish to offer pre-conference sessions for those who arrive early.  For instance, the Committee could offer CPF an early conference session from 1-5 on Sunday and provide CPF with all of the proceeds from the session.

- Remember to include the Student mini-Conference and Student Awards Lunch on the Sunday before the conference starts.

- The VP of Professional Development shall coordinate with National APA to obtain CM credit for conference sessions and programs. The VP will also ensure that CM credits are listed in the conference program.

- Remember; be creative and think outside of the box.  Sessions can and should be inspirational.  The programs are the Conference!

d.	Mandatory APA CALIFORNIA BOARD PROGRAM 	SESSIONS

And LIAISONS WITH AFFILIATED GROUPS

The Conference Program Committee must include the following sessions in the conference program.  The Conference Committee must contact the identified moderator to finalize the title, date and time of the session when all other session moderators are contacted.  The VP of Conferences will be responsible for finding meeting rooms, but not for program announcements for any of the sessions listed below that are requested after the date that all other moderators are required to finalize their session program.  Additional sessions submitted by the following designated organizations that are beyond the number of sessions listed below will be at the discretion of the Programs Committee.

- President’s Meet APA California Leadership Reception (Contact:  President) – One session.

- Special Chapter Session:  (Contact: President or any Vice President)

The board reserves the right to add one special session if it 	determines such as session is needed.

Legislative Update and Hot Legislative Topic (Moderator:  Vice President, Policy and Legislation and APA California Lobbyist) – One Legislative Update session and one Hot Legislative Topic session. Note: These sessions shall be treated as regular conference sessions and fully advertised in the conference materials. The Chapter Conference Committee shall not schedule other leg updates or similar hot topic sessions that will compete with these sessions.

- Planning Commissioner Session (Moderator:  Planning Commissioner Representative) – One session.

- AICP Training (Moderator:  Vice President, Professional Development) - One session.

- CPF Sessions (Moderator:  CPF President) - Two sessions.

- California Planning Roundtable Programs (Moderator:  CPR President) – Two sessions.

- Planners Emeritus Network Program (Moderator:  PEN President) – One session.

The VP of Conferences will act as the liaison and point of contact for the Board and affiliated groups for all conference questions and coordination of affiliated group events.  Each affiliated group (Planning Roundtable, CPF, PEN) is required to appoint a conference liaison who will act as the one point of contact for the conference committee in setting up group events and activities.  If no liaison is appointed, the President of the affiliated group will be the conference liaison.

E.	MANDATORY SPECIAL EVENTS

The VP of Conferences must also plan for and include in the Conference Program the following special events:

1.	Awards Ceremony

A suitable event must be planned for presentation of the annual awards during the conference.  The time, location, menu, theme and decorations are the responsibility of the Chapter VP of Administration/State Awards Coordinator.  The program and the awards are the responsibility of the VP of Administration/State Awards Coordinator and are under his/her direction. The configuration of the stage/head table, etc. shall be done in coordination with the Vice President, Administration.  There shall be provision for a PowerPoint presentation or Video to be shown during the presentation (which will be coordinated by the Vice President/State Awards Coordinator).

Cal Planner publishes an insert for the awards that is generally distributed as a “program” at the ceremony. A program is generally distributed as part of the awards ceremony –  Responsibility for dissemination of the awards insert  programis the responsibility of the Vice President, Administration/State Awards Coordinator.  Contact the Design/Graphics/Publication Consultant to develop the program printing schedule.

2.	CPF Fundraiser and Auction

Time must be made in the program for the CPF fundraiser and auction.  The VP of Conferences shall contact the CPF Board Conference Liaison as soon as possible to coordinate these activities.  The nature of the fundraiser is determined by CPF, which is responsible for all arrangements including the cost of any refreshments or entertainment provided, except for time in the program and designation of a prominent location at the conference which shall be provided by the VP of Conferences with approval of the CPF Board Conference Liaison.

3.	Student Conference and Student Awards Ceremony

The VP of Conferences shall work with the APA California Student Representative, University liaison and CPF Conference Liaison to develop and schedule a Student Conference and sessions and student awards lunch that shall be held the Sunday afternoon before the opening reception.

F.	Required Meeting Rooms for Leadership Meetings

A meeting room must be scheduled during the conference for the following leadership meetings.  The Conference Consultant shall schedule the time and location of the meetings in coordination with the individual noted below who is responsible for organizing the meeting.  The time and place of the meetings must be listed in the conference program.  The Conference Consultant must contact the identified Board member to finalize the title, date and time of the session when all other session moderators are contacted.  The Conference Consultant will not be responsible for finding meeting rooms or program announcements for any of the sessions listed below that are requested after the date that all other moderators are required to finalize their session program.

- APA California Board of Directors (Contact: APA California Administrative Director) – This meeting must be scheduled the day of the opening reception.  Note:  The Board liaison must contact the Administrative Director Tom Stefan (916-737-2372, sgassoc@msn.com) at least one week prior to the conference to coordinate the food and refreshments for the APA California Board meeting.

- California Planning Foundation Board of Directors (Contact:  CPF President)

- California Planning Roundtable (Contact:  Roundtable President)

- Planners Emeritus Network (Contact: PEN President)

- Note: This is now a mandatory leg update session (scc c, d) Chapter Student Representative with Section Student Representatives and Student Conference Attendees (Contact:  Chapter Student Representative)

- Standing Conference Committee (Contact:  President Elect/Immediate Past President)

G.	Continuing Education Credit/Certification Maintenance - Review the material in this section and also check the current Certification Maintenance information on AICP’s website. The material in the conference manual was prepared in June of 2009.  Elements of the CM program will change at the discretion of the APA. The Chapter’s Vice President for Professional Development can assist in explaining the requirements.

- Sending Out and Posting the Call for Sessions

- When seeking program sessions, make sure you’ve got the   important, hard-to-get credits lined up as part of the program.  Right now, it’s the legal and ethics 1.5 CM credits that people need.  Plan multiple sessions in big rooms!

- Use the CM data collection template for gathering information.   Use the multi-part activity template data collection form when you ask moderators to complete the session. This is mandatory. .  Using the template saves time and ensures you gather the proper information.

- Before the Conference

- Select a point of contact. The “point of contact” for conference CM credits should complete the CM template form for CM submission.  The actual work of inputting the data into the CM system will be done by the Chapter.

- Ensure the substantive content of the event is complete.  Once an event is registered for CM credit, the substantive content of the event cannot be altered. If substantial changes in content are made, the event must be re-registered as a new event.

- Select an evaluation mechanism.    CM providers are required to use evaluation mechanisms to assess each event or activity’s quality and relevance to its purpose or objectives. The type of evaluation form recommended in 2009 follows.

- Select a mechanism for recording attendance.  From time to time APA will audit provider records. If your event (e.g. conference) has several activities, one registration list will suffice – for example, providers are not required to have sign-in sheets at each session, but should retain a master list of all registrants.  Data collected at time of registration must include whether someone is an AICP member or not and that data needs to be tracked on the list of participants.  After the conference, you will be expected to send multiple reminders to AICP members who attended the conference that they should go on-line to register for their CM credits.

- Maintain verification records for two years. Should the provider be audited, they will need to produce participant registration information.

- Register your event.  Once the template data is available, the Chapter will log it on to the national CM system. Remember, the approval process takes up to three weeks.  You will want to do this as soon as possible so that you can market your event as having CM credits awarded.

- Use national resources to help promote the conference.  There are CM branding and marketing strategies laid out on the APA website.

- Lay out the program to include the number of CM approved credits hours for each session or event in the conference program.

- During the Conference

- Maintain paper or electronic copies of event registration.

- Distribute and collect event evaluations.  Remember to obtain an evaluation from each participant.

- Notify your attendees on how to register CM credit in their event log. You can provide this info at the conference itself as well as sending subsequent reminders.

- After the Conference

- Maintain the registration log and evaluations for two years. CM staff may occasionally conduct an audit of CM activities. Copies of registration and evaluations will be required.  Stefan/George will maintain the paper evaluation records and will also hold on to the electronic registration as well.  You need to make sure a final copy including all on-site registrations is sent to them.

- Send reminders to AICP members who attended the conference to log their credits.

E.  Other Professional Development Activities at the Conference

Several sessions will have to must be slotted at the conference to help members with professional development activities including.

- AICP Exam Prep Session – during conference prime time

- Meeting of the Section PDO’s  -- generally late in the day

- Meeting of the Fellows of AICP – will vary, but probably not during conference prime time.

F.  Contact APA California Continuing Education Coordinator for Credit Information

The Conference Committee must contact the APA California Continuing Education Coordinator to obtain Continuing Education Credit from AICP, MCLE credit, and APA California Continuing Education credit for sessions at the conference.

Action Items in this section:

Action Item

Board Approves Conference Theme

Action Item

Board Approves Final Draft Program

Action Item

Conference Program Committee Reviews Session Guidelines

Action Item

Contact Design/Graphics/Publications Consultant ASAP

Action Item

Ensure E-mail Blasts Use Most Up-To-Date National Member E-mail List

Action Item

Submit Conference Booklet No later than 2 months Prior to Conference to Design Consultant

Action Item

Provide Required Meeting Rooms for Leadership Meetings

Action Item

Contact Continuing Education Coordinator for Credit Information and List Credits in Program

Action Item

Advertise the Conference in Cal Planner, Section Newsletters and on the Web

Action Item

Contact the Design/Graphics/Publication Consultant by January of the Year of the Conference to Coordinate Conference Publications

VI.	ADVERTISING THE CONFERENCE

A.	Cal Planner

The following conference announcements are required to advertise the conference:

1.	One minimum half-page notice/article announcing the conference, or “Save the Date” notice, in the January/February issue of Cal Planner the year of the conference.  The notice/article shall be prepared by the Host Section for approval by the VP of PIPublic Information. NOTE:  The notice/article shall also be posted on the APA California website.

The Cal Planner conference ads will be printed in Cal Planner at no cost to the conference committee but the Conference Host Committee must prepare the text and graphics.

2. Two registration/conference information packets (four-page insert brochure) shall be published in Cal Planner (one for release prior to early registration and one for release on month prior to the conference).  NOTE:  The two registration/conference information packets shall also be posted on the APA California website.

Pre-registration materials will be published in the Cal Planner.  The VP of Conferences in consultation with the VP of Administration must contact the Cal Planner Design/Graphics/Publication Consultant	to coordinate the timing and number of 	pages of the notices/articles/ads and the conference brochure no later than January of the year of the conference.

B.	Section NewsletterS

The VP of Conferences and VP of Public Information shall provide Section Newsletter Editors with conference notices/articles and materials that are to be included in the Section newsletters and on the Section websites.

C.	APA CALIFORNIA Website – CONFERENCE POSTING 	PROCESS

The Conference Coordinator Consultant shall work with the VP of Conferences and the Section Conference Host Committee to develop and post on the APA California website the conference announcement, registration materials, conference registration application, call for papers, articles, and other conference items as determined by the VP of Conferences.  The Conference Coordinator Consultant will be provided with the web administrative access code and shall be the designated point person for the Conference Committee responsible for working with the Chapter Information Technology Director and posting any materials on the APA California website.

The following conference announcements must be posted on the APA California website.  These are the same announcements prepared for Cal Planner (see VI.A).

1.	One article announcing the conference, or “Save the Date” notice, in January/February of the year of the conference.

2.	A registration/conference information packet (four-page insert brochure).

- CONFERENCE WEBSITE

- SEND E-mails Directly to APA CALIFORNIA Members

At least two e-mails to members (one early and one final announcement and registration instructions) shall be sent directly to APA California’s members by direct e-mail using the most up to date National e-mail list.

The APA California e-mail distribution policy requires e-mails to members to provide the recipient with the opportunity to opt out of future e-mails with an automatic subscribe or unsubscribe option in the e-mail.  E-mails must include the sender’s contact information and postal address.

The Standing Conference Committee will work with National APA to correct outdated e-mail addresses.

Action Items for this section:

Action Item

Send at Least 2 Direct  E-mails to APA California Members

Action Item

Provide Complimentary and Contracted Display Space and Other Requirements

Action Item

Contact Director of Administration for Updated Display Space and Contract Info

VII.	EXHIBIT BOOTHS/DISPLAY SPACE

A.  Complimentary AND CONTRACTED Display Space

The following receive free display space in the exhibit hall or exhibit space.  Except for the APA California booth and table, which should be visible at or near the entrance to the exhibit hall or exhibit space, the space provided does not need to be premium space, but should be included in the regular exhibit location. Because As these agreements are updated frequently, the Conference Coordinator Consultant shall contact the Director of Administration to determine if any other reciprocal agreements have been added or deleted from this list, or updated.

COMPLIMENTARY DISPLAY SPACE

- APA California - (booth and table) - contact Director of Administration

- Following Year’s APA California Conference - (table) - contact Conference Committee chair

- Best, Best & Kreiger - (table) - contact Marco Martinez at 949-263-2600

- AEP - (table) - contact Director of Administration

- APA California Historian – (table) – contact Betty Croly at 510-841-0249

- Cal State Northridge – (table) – contact ?????

CONTRACTED DISPLAY SPACE AND OTHER CONFERENCE REQUIREMENTS

- CAL TRANS:

  - 2 tables or 2 booths

  - 5 conference sessions

  - 2 full complimentary registrations (includes meals)

  - 1 full page ad in the conference program

  - Recognition during conference

  - List Cal Trans as premier sponsor in conference program

  - Include Cal Trans in list of sponsors in Sponsors’ PowerPoint presentation shown during conference

Action Items in this section

Action Item

Include ADA Notice in Registration Information and Mailers

Action Item

Reserve Hotel Rooms for APA California Board and 5 Extra Rooms

Action Item:

Provide Conference Registrants with Written Confirmation of Registration

VIII.	OTHER MANDITORY ITEMS

A.	ADA COMPLIANCE AND NOTICE IN REGISTRATION 	MATERIALS

For ADA compliance, the Conference Committee shall include notice in registration mailers indicating that the conference hotel is APA compliant and that reasonable accommodations will be made if a registrant provides early indication of need.

B.	RESERVE HOTEL ROOMS FOR APA CALIFORNIA BOARD

A block of rooms shall be set aside for Board members and staff at the main conference hotel.  A deadline for confirming these reservations will be established by the Conference Coordinator and the Board and staff informed of the deadline and steps necessary to ensure that they have rooms in the main conference hotel.  The Conference Coordinator shall request that the hotel provide upgrades (view, suites, larger rooms) for Board members’ rooms.

C.	EXTRA HOTEL ROOMS

The Conference Coordinator shall reserve an additional five rooms for unanticipated guests, press or last-minute Conference Committee use.

D.	REGISTRATION CONFIRMATION

Conference registrants must be sent a written confirmation within a reasonable time of receipt of their registration.  The confirmation can be sent via e-mail or regular mail.

Action items for this section:

Action Item:

Thank the Conference Host Committee during Major Conference Event

Action Item:

Introduce APA California Board at Major Conference Event and Provide Seating at Head Table at Event

Action Item:

Provide Board Members with Registration Packets during Board Meeting

Action Item:

Provide Ribbons for Name Badges for Leadership and Speakers

IX. AT THE CONFERENCE

A.	THANK THE CONFERENCE COMMITTEE

The Conference Host Committee shall be officially introduced and thanked during at least one major conference event.

B.	HEAD TABLE FOR APA CALIFORNIA BOARD

At least once during the conference there must be an opportunity for the APA California Board to be introduced to the membership.  This is generally done by seating the APA Executive California Board at a head table during a plenary lunch or session.

The Board members shall be notified by the VP of Conferences at the Board meeting when they will be expected to be at the head table (or other event where they will be introduced or play a part).  The VP of Conferences will coordinate which Board members will be in attendance so that the head table can be set to seat only those who will be present.

C.  APA CALIFORNIA BOARD REGISTRATION PACKET DISTRIBUTION

The Conference Coordinator Consultant shall provide the APA California Board members’ and staff with their registration packets sometime during the APA California Board meeting.

D.	RIBBONS FOR NAME BADGES FOR LEADERSHIP AND 	SPEAKER IDENTIFICATION

Different colored ribbons or other identification shall be provided at registration, to be attached to the badges of the following groups:

- Conference Host Committee members

- APA California Board members

- California Planning Foundation Board members

- Planners’ Emeritus Network Board members

- California Planning Roundtable Board members

- Speakers

- Students

- Planning Commissioners

- Award winners

- Staff (when staff are also speakers, they should be provided with both ribbons)

- National Board members

Action items for this section:

Action Item:

Conference Chair Participates in Standing Conference Committee Meeting at Conference

X.  STANDING CONFERENCE COMMITTEE

The Standing Conference Committee is chaired by the President and is composed of the following members: Host Chair of the previous year’s conference; Host Chair of the current year’s conference; Host Chair of the following year’s conference; President Elect/Immediate Past President; Vice President for Conferences; Executive Director, and Director of Administration.

The Committee shall meet during the conference each year or within one month following the conference to facilitate coordination between various years’ conference committees, to discuss issues related to the annual conference and to review Board Conference Requirements and make any recommendations it deems necessary concerning the Requirements or other conference policies to the Board.

The Committee shall meet by conference call during the year as necessary to keep the Conference Handbook updated and the Conference on track.

Action items in this section:

Action Item:

The Conference Committee Shall Provide Information to Include in Conference Handbook within Three Months Following the Conference

Action Item:

Work with Standing Conference Committee, President and VP for Administration and APA California Board to Keep Conference Handbook Updated

XI.  UPDATING AND DISTRIBUTING THE CONFERENCE HANDBOOK

VP of CONFERENCES:

Within three months following the conference, the  VP of Conferences shall:

- PROGRAM.  Add the conference program to the official Conference Binder.

- CONFERENCE SUMMARY.  Provide a summary of the Conference, including the budget, how many rooms were used at the conference hotel, conference attendance broken down by registration categories, and the attendance at specific conference events and mobile workshops.

- RECOMMENDATIONS TO THE BOARD AND STANDING CONFERENCE COMMITTEE.  Make recommendations to the Board and Standing Conference Committee concerning changes or clarifications to the policies contained in the APA California Board Conference Requirements Handbook. The APA California Board shall approve any changes made to the APA California Board Conference Requirements Handbook.

STANDING CONFERENCE COMMITTEE:

The Standing Conference Committee shall be responsible for collecting input and updating the Handbook except for the APA California Board Conference Requirements (which shall remain the responsibility of the Board) and distributing the updated Conference Handbook to the upcoming Conference Committee. All major changes to the Handbook shall be approved by the Board.

PRESIDENT AND VP CONFERENCES:

The APA California President and Vice President for Conferences shall be authorized to make interpretations and minor amendments to the manual without Board approval.

APA CALIFORNIA BOARD:

All major changes to the APA California Conference Handbook Board Conference Requirements shall be approved by the APA California Board.

APPENDICES

APPENDIX A

CALIFORNIA CHAPTER,

AMERICAN PLANNING ASSOCIATION

ASSOCIATION AND SECTION Legal and Insurance ACTIVITY GUIDELINES

Because of the need to protect ourselves against the threat of preventable lawsuits and because of regulations from our insurance carrier, we are to follow these guidelines in the planning and conduct of Association and Section activities:

1.	Activities other than normal meetings of members are to receive prior approval from the Board, or the Board’s designee.  This is to include Association and Section sponsorship or endorsement of activities which present excessive risk of harm for members and guests.  A white water rafting excursion is an example.

2.	Endorsement or distribution of products and services are also to receive prior approval.  This includes acceptance of products and services as donations for use in fund raising.

3.	The Association and Sections are not to sell or distribute alcoholic beverages.  If alcohol is to be part of a meeting or other activity it should be served by a caterer providing evidence of adequate insurance, or by the service staff of the facility in which the meeting/activity is to be held.

4.	Any transportation arranged in conjunction with an activity is to be provided only by a transportation company holding a valid PUC certificate of operation and in force vehicle liability insurance, both of which are to be evidenced by a current Certificate of Insurance.

Conduct of regular activities which fall within these guidelines do not require prior approval.  If there is any question as to the acceptability of an activity, contact the Association office.  A minimum of three (3) weeks advanced notice is to be given to allow the APA California Director of Administration to contact our insurance carrier to determine the acceptability of any activity and/or whether any additional premium will be charged.

Appendix B

Conference coordinator and registration responsibilites

Conference Coordinator Consultant

Lynne Bynder, Meetings Xceptional

VISION STATEMENT:  Each conference consultant shall be responsible to support and report directly to the APA California Board and shall support the Conference Committee as outlined in the contract.   The Executive and Administrative Directors are responsible for the general oversight of the consultant contracts and are required to report any issues with contractors to the APA California President and Board.

Meetings Xceptional is a full service meeting and event management company contracted by the APA California Board to provide the following services to the APA California Board and Section Host Conference Committee.

I.	REPORTS TO APA CALIFORNIA BOARD

- Provide the APA California Board with a report on the status of each area of responsibility as outlined below, including an update of the current financials for the Conference in conjunction with Stefan/George Associates, and any issues or concerns.

- Provide the reports to the APA California Board and Conference Committee at the following intervals:

- An e-mailed report one year before the conference.

- A verbal and written report (as an attachment to the Board agenda) at the first APA California Board meeting of the year.

- A verbal and written report (as an attachment to the Board agenda) at the summer APA California Board meeting.

- An e-mailed brief synopsis at the beginning of each month after the summer Board meeting until the conference begins.

- A verbal report at the conference Board meeting.

- A final verbal and written report (as an attachment to the Board agenda) at the first APA California Board meeting, including any recommendations for changes or clarifications to the Conference Handbook.

II.	RELATIONSHIP WITH CONFERENCE COMMITTEE

- Obtain approval by either the Conference Chair or appropriate Conference Committee Chair of all conference decisions as specified in this scope of services.

- Complete specific tasks in the jurisdiction of a specific Conference Committee Chair in conjunction with the appropriate conference chair that handles specific conference issues.  Any materials produced for the conference must first be reviewed and approved by the Conference Chair or Conference Committee Chair, as appropriate.

### III.	REGISTRATION/ADMINISTRATION

- Obtain/negotiate contract for APA CALIFORNIA-approved on-line registration company based on budget and obtain approval of contract (to be provided by APA California) by the APA California Board and APA California attorney.

- Prepare continuous e-blasts for the registration company to potential attendees advertising the conference using the most up-to-date e-mail list from National each time the e-mails are sent to members.

- Provide information to the registration company to develop/update on-line conference registration form in accordance with the budget income line items, with the approval of the Conference Committee.

- Manage the registration company pre/post and on-site.

- Report and update Conference Committee and Board on Registration progress pursuant to report timeline in I, above.

- Coordinate name badges with the registration company.

- Provide Committee/Board with conference progress updates as outlined in I, above.

- Prepare a Conference Budget based on previous conferences and committee recommendations, with approval of the Conference Committee and update accordingly to Budget Chair/State office. The budget line items will be uniformly represented between the adopted budget, the registration company, and the financial accounting consultant (see Appendix L).

- Prepare a Conference Timeline with approval of the Conference Committee and update accordingly.

- Follow APA California Conference Handbook instructions and requirements.

- Attend monthly Conference Committee meetings.

- Meetings Xceptional will serve as the official APA California Conference Office and answer all correspondence related to conference and/or forward to designated Committee Chair.

### IV.	PR/CONFERENCE PROGRAM & SIGN DESIGN

- Work collectively with Conference Graphic Designer on design of forms, programs, signage to portray a professional conference image.

- Work collectively with Conference Committee for Conference Theme and logo.

- Work collectively with APA California webmaster on Conference website and send prepare/forward updates as outlined in timeline.

- Develop and prepare pre-promotion booth, and booth handout items for following-year conference, with approval of the Conference Committee.

- Develop and distribute conference documents, including Exhibitor, sponsorship, advertising, pre-registration brochure and Cal Planner Conference articles, with approval of the Conference Committee.

- Contact Conference Graphic Designer for local graphic images to use in conference collateral and distribute to Committee and Graphic Designer.

- Meet Cal Planner production deadlines.

### V.	EXHIBITOR/SPONSORS/ADVERTISERS

- Assist the Conference Committee with promoting, pre-selling and coordinating Exhibitors, Sponsors and Advertisers for conference.

- Issue RFP for Conference Decorator to handle booth set-up/tear-down and on-site exhibitor services, and share proposals with Conference Committee for selection of Conference Decorator.

- Report monthly revenue progress from Exhibits/Sponsors/Advertisers to Committee through the Exhibit/Sponsor Chair.

- Coordinate pre-promotion of upcoming conference forms each year, with approval of the Conference Committee.

- Ensure that Exhibitors, Sponsors and Advertisers send fees to the APA  California Conference Accounting Contractor to deposit in APA California Conference account.  This information should be included on all materials produced for Exhibitor, Sponsors, and Advertisers.

- Responsible for overall formal correspondence with all exhibitors and sponsors including coordination of ads to program designer.

- Responsible for coordinating all final details for on-site implementation pertaining to Exhibitors, Sponsors and Advertisers.

VI.	HEADQUARTER HOTEL/OVERFLOW HOTEL, OFF-SITE FACILITIES

- Issue RFP from hotels on behalf of APA California.

- Negotiate hotel contract on behalf of APA California pursuant to conference guidelines.

- Responsible for food and beverage negotiations and final requirements, with approval of the Conference Committee.

- Responsible for AV requirements and negotiations necessary for conference, with approval of the Conference Committee.

- Responsible for setting up and managing room reservations, and report progress to Board and conference committee pursuant to I, above.

- Responsible for securing rooms and special guest reservations.

- Responsible for all on-site logistics pertaining to the hotel and any off-site facilities, including ensuring that session rooms are set up appropriately and that the designated AV and other requirements are in place prior to the sessions, in conjunction with the Conference Committee

- Assist the Conference Committee with off-site venue proposals and coordination.

### VII.	MISCELLANEOUS CONFERENCE SUPPORT

- Issue RFP and coordinate Transportation for Mobile Workshops & off-site events.

- Arrange for attendee airline discounts and have posted on website.

- Arrange for attendee rental car discounts and have posted on website.

- Arrange for attendee child care and have posted on website.

- Present, receive pricing and order conference give-a-ways, on-site pre-promotion items, conference bags, ribbons, badge holders, Board/Keynote speaker gifts.

- Order all on-site local brochures for conference pertaining to Things-to-Do for current and incoming conference working with the APA California Conference Graphic Designer.

VIII.	MONIES TO APA CALIFORNIACONFERENCE ACCOUNTING CONSULTANT

(	Ensure all conference monies are sent directly to Stefan/George Associates, APA California conference accounting consultant.

SCOPE OF SERVICES

CONFERENCE REGISTRATION SERVICES

VISION STATEMENT: Each conference consultant shall be responsible to, support and report directly to the APA California Board, and shall support the Conference Committee as outlined in the contract. The Executive and Administrative Directors are responsible for the general oversight of the consultant contracts and are required to report any issues with contractors to the APA President and Board.

Summary of Services Provided by ThinkREG:

DATES: September 13 – 16, 2009

LOCATION: Squaw Creek

AUDIENCE: 1,400 attendees (projected)

SERVICES: ThinkREG will provide APA with the following items:

• Online Registration and Reporting

• Payment Processing

• Badge Printing and Production

• Onsite Registration Management

THINKREG SHALL PERFORM THE FOLLOWING IV SERVICES:

I. Registration and Reporting

Registration Management Services:

Results Delivered, LLC/ThinkREG Registration Management Services include:

 Reports the client asks to run and emailed by Results Delivered, LLC/ThinkREG on the clients behalf

 Registrant receipt requests processed by Results Delivered, LLC/ThinkREG on the clients behalf

 Registrant changes processed by Results Delivered, LLC/ThinkREG on the clients behalf

 Updating registrant survey or demographic information

 Updating registrant payment information

ThinkREG will manage the attendee registration and web-based registration services, including:

• A web link for web-based registration. ThinkREG will load the customized online Registration Page on our secure server and link the page to the conference web site. The online page will

maintain the same “look and feel” as your overall web site. In addition, ThinkREG will assist with creation of separate pages and reporting for attendees, speakers, and staff registration.

• Real-time, on-line registration reports. All report templates are available to you in a password-protected section of the ThinkREG web site. All reports can be exported in multiple file formats, all reports are real-time. Reports can be viewed within a web browser, or downloaded to Microsoft Excel.

II. Payment Processing

• Payments made by check will be handled by the APA Conference Accounting Consultant. The client will also handle deposits for these transactions, as well as account reconciliation.

• Payments made online via Credit Card will be deposited into the ThinkREG merchant account. ThinkREG will handle reconciliation for payments deposited to ThinkREG merchant account. ThinkREG will make three (3) attempts to charge declined cards, as well as reasonable attempts to resolve “charge-backs”. Payments online via credit card will be made via the discount rate and payment schedule below.

| Credit Card Processing Fees: Discount Rate Visa/MC/Discover | 4.25% |
| --- | --- |
| Discount Rate American Express | 4.29% |
| Setup Fee for ThinkREG merchant account usage | $0.00 |
| Per Transaction Fee | $0.00 |

Credit Card Payment Schedule:

Credit card payments shall be remitted to APA pursuant to the following schedule:

1) Credit card payments received between the 1st and 15th of the month will be remitted to APA by the 7th day of the following month; and

2) Credit card payments received between the 16th and the last day of the month will be remitted to APA by the 21st day of the following month.

All payments submitted to the APA Conference Accounting Consultant shall include a full explanation of the transactions included in the payment, including name of persons making the transaction.

If an attendee contests a charge, a $35.00 chargeback fee will be assessed to client for each occurrence. Results Delivered, LLC/ThinkREG will attempt to recoup the charge by contacting the disputing party and the credit card company within the first five business days of receiving the chargeback notification. If after three reasonable attempts the chargeback is not reversed, Results Delivered, LLC/ThinkREG will turn the case over to the client for further follow up. Results Delivered, LLC/ThinkREG will not be financially responsible for covering contested charges.

III. Badge Printing/Production

 ThinkREG will provide conference badge stock (4”x3”, 4-color logo, white paper).

 ThinkREG will print the conference logo, attendees first and last name, attendee’s company, and bar code for scan check-in. In addition, ThinkREG will provide backup basic clear plastic badge holders. Lanyards are also available. APA must provide all artwork/graphical elements for badge stock production in the format requested by ThinkREG.

IV. Onsite Registration and Support

ThinkREG will provide onsite staff to coordinate onsite conference registration, badge production, and payment processing (if APA is utilizing ThinkREG for payment processing – also requires high speed Internet connection), including:

 One Registration Manager responsible registration set-up and operation of the registration desk

 One Network Engineer responsible to set-up the registration network

 Local Registration Staff:

6 Registration Counters (Peak Days)

Saturday – Travel/Setup

Sunday – Reg Open, 9 am – 6 pm

Monday – Reg Open, 7 am – 6 pm

Tuesday - Reg Open, 7 am – 6 pm

Wednesday – Reg Open, 7 am – 2 pm

V. Terms and Conditions .

 In addition, APA must provide ThinkREG with its Federal Tax ID #. ThinkREG will also need the necessary information to conduct a APA credit check prior to the registration site going live.

 ThinkREG agrees to all credit card company terms and conditions for payment processing – thus – APA is required to do the same. By signing this agreement, APA also agrees to the credit card company terms and conditions (if APA wishes to receive a copy of these terms and conditions, ThinkREG will supply it upon request). APA also agrees to the following specific credit card payment processing terms and conditions:

Obtain the Cardholder’s Signature: In a face-to-face environment, the card acceptor must give the cardholder the option of a signature-based transaction. Unless the cardholder uses a PIN, the cardholder must sign a receipt.

Signature Not Required: Note - This requires proof of delivery, such as a FedEx tracking number, or USPS tracking number showing conference materials were delivered to the BILLING ADDRESS OF THE CARDHOLDER.

Give the Cardholder a Copy of the Receipt: The card acceptor must provide the cardholder with a true and completed copy of the transaction.

If APA does not follow the credit cards terms and conditions, ThinkREG will not be financially responsible for covering contested charges or “charge-backs”. In all cases, APA will be required to cover costs/refunds of such occurrences.

APPENDIX C

Conference Accountant Management Consultant Responsibilities and Conference Financial Requirements:

Tom Stefan and Francine Farrell, Stefan/George Associates

VISION STATEMENT:  (Vince will provide statement to specify for each consultant how that consultant is expected to work with and support the Board and Conference Committee, and to specify that the Executive and Administrative Directors are the CEO’s that oversee the consultant contracts and any problems with those contractors.)

Stefan/George Associates is a full service accounting and association management company contracted by the APA California Board to provide the following services to the APA California Board and Section Host Conference Committee.

Stefan/George Associates will maintain all financial records as follows: See Appendix G for detailed information.

- Keep a full and complete record of Conference finances:

  - Receive, deposit and disburse Conference funds.

  - Coordinate with conference coordinator the sponsor invoicing and payments

  - Process account payables and receivables

  - Reconcile bank statements

  - Reconcile check payments from registration company to budget line items

- Prepare final financial reports:

  - Profit and Loss Statement

  - Balance Sheet

  - Transaction by Account Detail

  - Trial Balance

- Prepare periodic financial reports upon request by Committee, including a final conference financial report to the Board.

- Send out 1099s to vendors.

- Maintain two conference checking accounts with a minimum of $15,000 in each account to loan to the current and upcoming conferences for initial conference expenses.

The Conference Committee will provide to Stefan/George Associates as soon as they become available:

- Committee Roster.

- Conference Budget.

- Copies of all Contracts.

- Any checks received that are for the conference (i.e. Sponsors, Advertisers, Registrations paid by check, etc.).

- Original or copies of all vendor invoices/billings, which have been approved for payment and signed by the conference Chairperson or Treasurer.

  - Note on the invoice/bill which conference budget line item each expense is to be allocated towards.

- Any 1099 tax forms sent to the Conference Committee by vendors.

Conference Related Financial Policies

Conference Responsibilities

APA California (S/G) Responsibilities

Summary of Financial Responsibilities for Stefan/George Associates (S/G)

for APA California Conference –

The Conference Committee will need to provide to SG as soon as they become available:

- Committee Roster.

- Conference Budget.

- Copies of all Contracts.

- Any checks received that are for the conference (i.e. Sponsors, Advertisers, etc.).

- Original or copies of all vendor invoices/billings, which have been approved for payment and signed by the conference Chairperson or Treasurer.

  - Note on the invoice/bill which conference budget line item each expense is to be allocated towards.

  - Any 1099 tax forms sent to the Conference Committee by vendors shall be sent to Stefan/George Associates.

Stefan/George Associates will maintain all financial records to include: See Appendix G for detailed information.

- Keep a full and complete record of Conference finances:

  - Receive, deposit and disburse Conference funds.

  - Coordinate with conference coordinator the sponsor invoicing and payments

  - Process account payables and receivables

  - Reconcile bank statements

  - Reconcile check payments from registration company to budget line items

- Prepare final financial reports:

  - Profit and Loss Statement

  - Balance Sheet

  - Transaction by Account Detail

  - Trial Balance

- Prepare periodic financial reports upon request by Committee, including a final conference financial report to the Board.

- Send out 1099s to vendors.

- Maintain two conference checking accounts with a minimum of $15,000 in each account to loan to the current and upcoming conferences for initial conference expenses.

Conference Accounting Procedures

Stefan/George Associates is a full service accounting and association management company contracted by the APA California Board to provide services in accordance with the APA California financial policies, the conference manual, and other contracted conference providers.

- The conference committee will provide a contact list of the conference committee members as soon as it becomes available.

- The conference committee and/or conference coordinator will provide the conference budget as soon as it becomes available.

a.	The conference coordinator will work with the association management company and the registration company to ensure that each registration budget line item is associated with a registration company item.  There should be one registration item for each registration income budget income line item.  (See Appendix L)

- Conference committee reimbursed expenses: To obtain an expense reimbursement, fill in the Conference Committee Expense Claim Form (see page 52), attach copies of receipts for each item, except mileage, and send to Stefan/George Associates.  Any reimbursement request should be sent no later than one month after the conference.  Reimbursements cannot be made without a paid receipt.

  - Approval for reimbursement must be obtained from conference chairperson prior to making payment.

- All credit card payments are made through the registration company:

  - Credit card payments will be sent to Stefan/George Associates, minus the merchant fees, every two weeks.  With exception for the last payment which will be sent after the registration company has processed refunds and any charge backs but no later than 60 days after the conference.

  - An income breakdown should be sent with any check payment from the registration company (see page 53).  The breakdown of the income should be allocated to the appropriate budget line item.

- Registration payments by check are sent to Stefan/George Associates for processing:

  - Enter payment into QuickBooks Pro accounting software;

  - Enter check information in the registration record through the registration company’s website;

  - Send a copy of the paid receipt to attendee via e-mail; and,

  - Fax a copy of the paid receipt and check payment to conference coordinator.

  - Make deposits

  - Process Accounts Payables/Receivables

  - Invoice not paid Sponsors and make follow-up attempts to collect.

  - Invoice not paid Attendees and make follow-up attempts to collect.

- Reconcile monthly bank statements:

  - Review and reconcile the bank statement against the registration company’s report and the merchant statement for the same period.

- Financial reports will be sent to the conference chairperson monthly with a final report after receipt of the final check from the registration company.

  - Financial reports consist of:

    - Profit and Loss Budget vs Actual

    - Balance Sheet

    - Transaction Detail by Account

- Deposit State’s profit into general account and send profit distribution checks to Sections

- Send 1099’s to vendors by January 31st.

Provide final financial report and 1099’s received to tax consultant for tax filing each year.

Committee Expense Reimbursement Claim Form

Use form on next page.

# AMERICAN PLANNING ASSOCIATION

# C A L I F O R N I A   C H A P T E R

# Conference Committee Expense Claim Form

# Please print clearly.

Make check payable to:

Mail reimbursement to:

Name:

Company:

Address:

City/Zip Code:

DATE  OF	   			 	DESCRIPTION OF

EXPENSE	        			       EXPENSE			AMOUNTLINE ITEM#

| TOTAL |  |  |  |
| --- | --- | --- | --- |

Note:	Mileage, if applicable, is reimbursed at $0.55 per mile.   Copies of PAID receipts must be attached for all expenses, except mileage. Fax the completed claim form and copies of receipts to Francine Farrell at 916.456.1283.  To e-mail claim form and receipts, e-mail sgassoc@msn.com, attn: Francine Farrell.

PRINT NAME				                   				                 SIGNATURE

__________________________________________

Date							 						Telephone Number

Registration Company Check Payment Breakdown Form

Use form on next page.

APA California (fill in year) Conference

|  | Total Payment to APA California |
| --- | --- |
|  | Week ending: (Fill in Date) |
| Enter the fee breakdown in the appropriate line item. |  |  |  |
|  |  | Totals | Cumulative $ |
| Income | (Enter dates for check payment) | 7/18-7/24/03 | Totals to Date |
| 101 · Member - Early |  |  | 0.00 |
| 102 · Member - Standard |  |  | 0.00 |
| 103 · Member - Late/On-Site |  |  | 0.00 |
| 104 · Non-Member - Early |  |  | 0.00 |
| 105 · Non-Member - Standard |  |  | 0.00 |
| 106 · Non-Member - Late/On-Site |  |  | 0.00 |
| 107 · Member - One Day |  |  | 0.00 |
| 108 · Non-Member - One Day |  |  | 0.00 |
| 109 · Student - Full |  |  | 0.00 |
| 110 · Student - One Day |  |  | 0.00 |
| 111 · New Professional - Full |  |  | 0.00 |
| 112 · New Professional - One Day |  |  | 0.00 |
| 113 · Life Member - Full |  |  | 0.00 |
| 114 · Speaker - Com Session + 1-Day |  |  | 0.00 |
| 115 · Speaker - Comp Session + 2-Days |  |  | 0.00 |
| 116 · Exhibitor/Sponsor - Full |  |  | 0.00 |
| 117 · Exhibitor/Sponsor - 1 Day |  |  | 0.00 |
| 120 · Young Planner |  |  | 0.00 |
| 121 · Young Professional |  |  |  |
| 121 · Transportation |  |  | 0.00 |
| 118 · Processing Fee |  |  | 0.00 |
| 119 · Cancellation Fee |  |  | 0.00 |
|  |  | 0.00 | 0.00 |
| 301 · Mobile Workshop Tickets |  |  | 0.00 |
| 302 · Extra Meal Tickets |  |  | 0.00 |
| 304 · Opening Reception |  |  | 0.00 |
|  |  | 0.00 | 0.00 |
| Total Income: |  |  |  |
| Breakdown |  |  |  |
| Checks (company & personal) |  |  | 0.00 |
| Visa |  |  | 0.00 |
| MasterCard |  |  | 0.00 |
| Cash |  |  | 0.00 |
| Total: |  | 0.00 | 0.00 |
| Expenses |  | Totals | Cumulative $ |
| Credit Card Fees: |  | (Enter dates for check payment) | Totals to Date |
| Visa/MC (2.30% + $.30 ea. trans) |  |  | $0.00 |
| Visa/MC Non-Qualification Fees |  |  | $0.00 |
| Visa/MC Mid-Qualification Fees |  |  | $0.00 |
| Total Credit Card Fees: |  | $0.00 | $0.00 |
| Total Payment to CCAPA: |  |  | $0.00 |

APA California Conference Check

Or Vendor Payment Request Form

Use the form on the next page.

# AMERICAN PLANNING ASSOCIATION

# C A L I F O R N I A   C H A P T E R  L I F O

# APA CALIFORNIACONFERENCE CHECK OR VENDOR PAYMENT REQUEST FORM

# Please print clearly.

| Make Check Payable to: |  |
| --- | --- |
| Mail Payment to: |  |
| Name: |  |
| Company: |  |
| Address: |  |
| City/Zip Code: |  |

| Vendor | Description of Expense | Amount | Line Item # |
| --- | --- | --- | --- |
| Total |  |  |  |

The original or a copy of each vendor invoice must be included for payment.  Mail, email or fax completed form and back-up to Francine Farrell at APA CALIFORNIA, 1333 36th Street, Sacramento, CA 95816, sgassoc@msn.com or 916.456.1283 (fax).

| Print Name Date |  | Signature Telephone Number: |
| --- | --- | --- |

Appendix D

#### Sample Conference Budget

DO NOT PUT ON WEBSITE

Need to include examples from last several conferences.  Use the next page example.

| DRAFT APA California 2009 Conference Budget |
| --- |
| Draft Budget - As of March 5, 2009 |  |  |  |  |  |  |  |
|  |  | Qty | Cost | Income | Total |  |  |
|  | Revenue |  |  |  |  |  |  |
| 100 | REGISTRATION |  |  |  |  |  |  |
| 101 | Member - Early | 400 | $450.00 | $180,000.00 |  |  |  |
| 102 | Member - Standard | 100 | $475.00 | $47,500.00 |  |  |  |
| 103 | Member - Late/On-Site | 100 | $500.00 | $50,000.00 |  |  |  |
| 104 | Non-Member - Early | 50 | $525.00 | $26,250.00 |  |  |  |
| 105 | Non-Member - Standard | 25 | $550.00 | $13,750.00 |  |  |  |
| 106 | Non-Member - Late/On-Site | 25 | $575.00 | $14,375.00 |  |  |  |
| 107 | Member - One Day | 50 | $275.00 | $13,750.00 |  |  |  |
| 108 | Non-Member - One Day | 25 | $350.00 | $8,750.00 |  |  |  |
| 109 | Student - Full - Early |  |  |  |  |  |  |
| 109-B | Student - Full - Standard | 25 | $225.00 | $5,625.00 | Early, Standard and Late/On-Site categories are part of the Registration form and are how the WebRegPro will set up the registration forms and reports. All registration types/categories should be represented. | Also, New Professional categories (Early, Standard and Late/On-Site) has not been added to the Registration form. |
| 109-C | Student - Full - Late/On-Site |  |  |  |  |  |
| 110 | Student - One Day - Early |  |  |  |  |  |
| 110-B | Student - One Day - Standard | 25 | $150.00 | $3,750.00 |  |  |
| 110-C | Student - One Day |  |  |  |  |  |
| 111 | New Professional - Full - Early |  |  |  |  |  |
| 111-B | New Professional - Full - Standard | 25 | $325.00 | $8,125.00 |  |  |
| 111-C | New Professional - Full - Late/On-Site |  |  |  |  |  |
| 112 | New Professional - One Day - Early |  |  |  |  |  |
| 112-B | New Professional - One Day - Standard | 25 | $225.00 | $5,625.00 |  |  |
| 112-C | New Professional - One Day - Late/On-Site |  |  |  |  |  |
| 113 | Life Member - Full - Early | 10 | $225.00 | $2,250.00 |  |  |
| 113-B | Life Member - Full - Standard | 10 | $225.00 | $2,250.00 |  |  |
| 113-C | Life Member - Full - Late/On-Site |  |  |  |  |  |
| 114 | Speaker - Comp Session Plus One Day - Early |  |  |  |  |  |
| 114-B | Speaker - Comp Session Plus One Day - Standard | 10 | $275.00 | $2,750.00 |  |  |
| 114-C | Speaker - Comp Session Plus One Day - Late/On-Site |  |  |  |  |  |
| 115 | Speaker - Comp Session Plus Two Days - Early |  |  |  |  |  |
| 115-B | Speaker - Comp Session Plus Two Days - Standard | 10 | $450.00 | $4,500.00 |  |  |
| 115-C | Speaker - Comp Session Plus Two Days - Late/On-Site |  |  |  |  |  |
| 116 | Exhibitor/Sponsor - Full | 125 | $450.00 | $56,250.00 | If there will be Early, Standard and Late/On-Site categories with WebRegPro, they should also be included as additional budget line items. |
| 117 | Exhibitor/Sponsor - One Day | 50 | $275.00 | $13,750.00 |  |
| 118 | Processing Fee | 100 | $30.00 | $3,000.00 |  |  |  |
|  | Subtotal |  |  |  | $462,250.00 |  |  |
| 200 | SPONSORSHIPS |  |  |  |  |  |  |
| 201 | Event Sponsors | 5 | $3,000.00 | $15,000.00 |  |  |  |
| 202 | Meal Sponsors | 10 | $2,500.00 | $25,000.00 |  |  |  |
| 203 | Break Sponsors | 8 | $1,000.00 | $8,000.00 |  |  |  |
| 204 | Mobile Workshop Sponsors | 10 | $1,000.00 | $10,000.00 |  |  |  |
| 205 | Exhibit Booth Sponsors | 30 | $3,000.00 | $90,000.00 |  |  |  |
|  | Exhibit Tabletop Sponsors | 10 | $2,000.00 | $20,000.00 |  |  |  |
| 206 | Conference Bag Sponsor | 1 | $6,000.00 | $6,000.00 |  |  |  |
| 207 | Ad Sponsors | 3 | $600.00 | $1,800.00 |  |  |  |
| 208 | Major Sponsor | 1 | $30,000.00 | $30,000.00 |  |  |  |
| 208 | Conference Badge Holder Sponsor | 1 | $2,500.00 | $2,500.00 |  |  |  |
|  | Subtotal |  |  |  | $208,300.00 |  |  |
| 300 | MOBILE WORKSHOP/MEAL TICKETS |  |  |  |  |  |  |
| 301 | Mobile Workshop Tickets | 250 | $40.00 | $10,000.00 |  |  |  |
| 302 | Extra Meal Tickets (instead make this: Evening Reception) | 50 | $60.00 | $3,000.00 | Since each of the 'Extra Meal Tickets' are different prices you may want to consider making these line items and splitting out the $3K budget between them. |
| 302-B | Opening Reception |  | $95.00 |  |  |
| 302-C | Breakfast |  | $30.00 |  |  |
| 302-D | Lunch |  | $45.00 |  |  |
| 302-E | Brunch (Wed.) |  | $40.00 |  |  |
|  | Subtotal |  |  |  | $13,000.00 |  |  |
| 400 | CONFERENCE ADVANCE FUNDING |  |  |  |  |  |  |
| 401 | Seed Money From State |  |  | $0.00 |  |  |  |
| 402 | Seed Money From Section |  |  | $0.00 |  |  |  |
|  | Subtotal |  |  |  | $0.00 |  |  |
| 500 | NON CONFERENCE REVENUE |  |  |  |  |  |  |
| 501 | Interest |  |  | $0.00 |  |  |  |
|  | Subtotal |  |  |  | $0.00 |  |  |
|  | TOTAL REVENUE |  |  |  | $683,550.00 |  |  |
|  | Expenses |  |  |  |  |  |  |
|  |  | Qty | Cost | Income | Total |  |  |
| 1100 | ADMINISTRATION (Pre-Conference) |  |  |  |  |  |  |
| 1101 | Meals and Expenses for Committee |  |  | $3,000.00 |  |  |  |
| 1102 | Phone, Fax, and Postage |  |  | $3,500.00 |  |  |  |
| 1103 | Conference Facility Deposit |  |  | $0.00 |  |  |  |
| 1104 | Miscellaneous Committee Expenses |  |  | $2,500.00 |  |  |  |
|  | Subtotal |  |  |  | $9,000.00 |  |  |
| 1200 | ADMINISTRATION (During Conference) |  |  |  |  |  |  |
| 1201 | Hotel Room Expenses and Conference Registrations |  |  | $7,500.00 |  |  |  |
| 1202 | Conference Insurance |  |  | $4,200.00 |  |  |  |
| 1203 | Board and Attendee Gifts |  |  | $3,000.00 |  |  |  |
| 1204 | Transportation Costs |  |  | $25,000.00 |  |  |  |
|  | Subtotal |  |  |  | $39,700.00 |  |  |
| 1300 | ADMINISTRATION (Post-Conference) |  |  |  |  |  |  |
| 1301 | Administration Fee (Meetings Xceptional) |  |  | $32,500.00 |  |  |  |
| 1302 | Registration Company |  |  | $25,000.00 |  |  |  |
| 1303 | Processing Fee |  |  | $3,000.00 |  |  |  |
| 1304 | Repayment of Section Seed Money |  |  |  |  |  |  |
| 1305 | Close Out Books/Audit |  |  | $500.00 |  |  |  |
| 1306 | Administration Fee (Stefan George Associates) |  |  | $2,500.00 |  |  |  |
|  | Subtotal |  |  |  | $63,500.00 |  |  |
| 1400 | OPENING EVENT |  |  |  |  |  |  |
| 1401 | Entertainment |  |  | $1,500.00 |  |  |  |
| 1402 | Food (Bars/Facility) | 800 | $80.00 | $64,000.00 |  |  |  |
| 1403 | Student Luncheon | 150 | $40.00 | $6,000.00 |  |  |  |
| 1404 | Diversity Summit | 300 | $30.00 | $9,000.00 |  |  |  |
|  | Subtotal |  |  |  | $80,500.00 |  |  |
| 1500 | FIRST DAY SESSIONS |  |  |  |  |  |  |
| 1501 | Breakfast | 800 | $30.00 | $24,000.00 |  |  |  |
| 1503 | Lunch | 900 | $45.00 | $40,500.00 |  |  |  |
| 1504 | Break PM | 800 | $15.00 | $12,000.00 |  |  |  |
| 1505 | Evening Reception (Room, Food, Entertainment) | 800 | $55.00 | $44,000.00 |  |  |  |
|  | Subtotal |  |  |  | $120,500.00 |  |  |
| 1600 | SECOND DAY SESSIONS |  |  |  |  |  |  |
| 1601 | Breakfast | 800 | $30.00 | $24,000.00 |  |  |  |
| 1603 | Lunch | 900 | $45.00 | $40,500.00 |  |  |  |
| 1604 | Break PM | 800 | $15.00 | $12,000.00 |  |  |  |
| 1605 | Evening Reception (Room, Food, Entertainment) | 800 | $55.00 | $44,000.00 |  |  |  |
|  | Subtotal |  |  |  | $120,500.00 |  |  |
| 1700 | THIRD DAY SESSIONS |  |  |  |  |  |  |
| 1701 | Coffee and Juice | 500 | $10.00 | $5,000.00 |  |  |  |
| 1702 | Brunch (Sponsored) | 700 | $40.00 | $28,000.00 |  |  |  |
|  | Subtotal |  |  |  | $33,000.00 |  |  |
| 1800 | MEETING ROOMS |  |  |  |  |  |  |
| 1801 | Registration and Exhibits (Conference Decorator) |  |  | $0.00 |  |  |  |
| 1801-B | Exhibit Hall Space Fee (Hotel) |  |  | $0.00 |  |  |  |
| 1802 | Audio Visual |  | $24,000.00 | $24,000.00 |  |  |  |
| 1803 | Keynote Speaker Honoraria and Expenses | 2 | $5,000.00 | $10,000.00 |  |  |  |
|  | Subtotal |  |  |  | $34,000.00 |  |  |
| 1900 | PUBLICITY MATERIALS |  |  |  |  |  |  |
| 1901 | Printing and Design - Final Program |  |  | $17,000.00 |  |  |  |
| 1902 | Postage and Envelopes |  |  | $500.00 |  |  |  |
| 1903 | Conference Registration Brochures |  |  | $3,500.00 |  |  |  |
| 1904 | Signage - Directional, Sponsor, Etc. |  |  | $6,500.00 |  |  |  |
| 1905 | Pre-conference Promotional Souvenirs |  |  | $2,000.00 |  |  |  |
| 1906 | Website |  |  | $2,500.00 |  |  |  |
|  | Subtotal |  |  |  | $32,000.00 |  |  |
|  | TOTAL EXPENSES |  |  |  | $532,700.00 |  |  |
|  | TOTAL REVENUE |  |  |  | $683,550.00 |  |  |
|  | TOTAL EXPENSES |  |  |  | $532,700.00 |  |  |
|  | Less Contingency |  |  |  | $50,000.00 |  |  |
|  | NET PROFIT |  |  |  | $100,850.00 |  |  |

Appendix E

Conference Design and Publication Management Consultant:

Dorina Blythe, GranDesigns

VISION STATEMENT:  (Vince will provide statement to specify for each consultant how that consultant is expected to work with and support the Board and Conference Committee, and to specify that the Executive and Administrative Directors are the CEO’s that oversee the consultant contracts and any problems with those contractors.)

GranDesigns is a full service design and publication management company contracted by the APA California Board to provide the following services to the APA California Board and Section Host Conference Committee.

GranDesigns will provide the following services for the  APA California Conference:

1. 	 Create original design template to be used in all printed materials.

2.	 Prepare all documents per vendor digital instructions.

3. 	 Obtain quotes for all projects.

4. 	 Monitor quality control for each project.

5.    Coordinate shipping and/or deliver personally.

7. 	 Format and forward all files for use on authorized web site.

8. 	 Coordinate ads for the conference program directly with all sponsors.

9. 	 Forward digital artwork to any authorized vendor that requires it.

10.  Provide reminder calls, emails, and faxes.

11.  Coordinate mail house services with Stefan/George Associates where applicable.

12.  Coordinate with Lynne Binder, Meetings Xceptional.

Meetings Xceptional will perform the following initial production functions on behalf of the APA California Conference Committee:

1. 	Format copy per GranDesigns specifications before submitting/publishing.

2. 	Write and edit article copy before submitting with the understanding that there will be 	editing during the design process.

3.  Coordinate conference programs, schedules and information directly with the appropriate chair, confirm information, then forward to GranDesigns.

4.	Keep to time schedule to avoid rush charges.

Appendix F

Recommended Committee Structure/

Roles and Responsibilities

[NOTE THIS INFORMATION IS OLD AND NEEDS TO BE UPDATED TO REFLECT CONFERENCE COORDINATOR – STILL NEED HING WONG TO TAKE A LOOK AT THIS ]

#### Conference Co-Chairs

- Overall management of conference

- Master scheduling

- Check list/ make sure things get done

- Provide assistance to subcommittees, as necessary

- Meeting Agendas

- Coordination during conference

- Coordination with APA California Board

- Coordination with Host Section Board

- Maintain mailing list of committee members

Section Director (often serves as Liaison to APA California Board)

# Facilities/Transportation Committee

- Coordinate with programs and special events committees

- Special Meeting rooms (APA California, CPF, CPR, Legislative Review, Chap Prez/Leadership Reception)

- Press Room

- Audio-Visual

- Room Set-Up

- Banquet Facilities

- Transportation Needs (Mobile Workshops, Special Events)

# Programs Committee

- Solicit session ideas

- CPR

- PEN

- AICP training

#### Student Programs Committee

- Work with the universities and programs committee to create a Student-only Day of Sessions

# Public Relations Committee

- Conference Registration Forms

- Conference Program

- Coordinate with APA California Public Relations Firms

- Press Releases/News Articles

- Signage

# Registration Committee

Sponsorships and Booths (Kurt and Collette)

# Administration/Finance Committee

- Adhere to the APA California Board’s Fiscal Policies

- Develop Budget

- Monitor Budget

- Approval Payment of Invoices

- Must Use QuickBooks Pro Accounting Software

- Meeting Minutes

# Special Events Committee

Opening Reception

Consultants Reception

CPF Auction

# Keynote Speakers Committee

# Mobile Workshops Committee

# Volunteers Committee

Mandatory Events

CPF Auction

Consultants Reception

Exhibit Booths

Opening Reception

Awards Lunch/Dinner

Optional Events

Golf Tourney

Tennis Tourney

Appendix G

### Conference Themes

| APA CALIFORNIA Conference Themes |
| --- |
| Year | Motto/Theme | Location |
| 2010 |  | Carlsbad |
| 2009 |  | Lake Tahoe |
| 2008 |  | Los Angeles |
| 2007 |  | San Jose |
| 2006 | Reinventing Suburbia | Garden Grove |
| 2005 | No Theme | Yosemite |
| 2004 | Planning for Tomorrow’s Bright Future | Palm Springs |
| 2003 | A Link to the Past, A Bridge to the Future | Santa Barbara |
| 2002 | PlanDiego | San Diego |
| 2001 | APA at the Confluence | Sacramento |
| 2000 | Reaching Out, Building Bridges | Long Beach |
| 1999 | Celebrating Diversity | Bakersfield |
| 1998 | Mirrors and Reflections | Costa Mesa |
| 1997 | Choices, Challenges and Change | Monterey |
| 1996 | The Heat is On | Palm Springs |
| 1995 | Redefining Paradise, California’s Challenge | Santa Barbara |
| 1994 | Edges, Borders, New Frontiers | San Diego |
| 1993 | Maintaining California’s Competitive Edge | Modesto |
| 1992 | Celebrate the Spirit of Planning | Pasadena |
| 1991 | On the Edge | Sacramento |
| 1990 | Glitz versus Glitches | Newport Beach |
| 1989 | Pacific Rim | San Jose |
| 1988 | Hard Choices | Palm Springs |

Appendix H

Evaluation Form For CM Sessions

[NAME OF EVENT]

EVALUATION FORM

| Overall, the event I attended met or exceeded my expectations: |
| --- |
|  | Strongly Agree | Agree | Neutral | Disagree | Strongly Disagree |
| 2. Event presenters met or exceeded my expectations: |
|  | Strongly Agree | Agree | Neutral | Disagree | Strongly Disagree |
| The presenters were knowledgeable about the workshop content. (Strongly Agree = 5, Strongly Disagree =1) Presenter 1 _______________________________ 5 4 3 2 1 Presenter 2 _______________________________ 5 4 3 2 1 Presenter 3 _______________________________ 5 4 3 2 1 |
| The presenters delivered their material well (Strongly Agree = 5, Strongly Disagree =1). Presenter 1 _______________________________ 5 4 3 2 1 Presenter 2 _______________________________ 5 4 3 2 1 Presenter 3 _______________________________ 5 4 3 2 1 |
| 5. The content of this event was: |
|  | Very Advanced | Somewhat Advanced | Intermediate | Somewhat Basic | Very Basic |
| 6. The event provided useful ideas or techniques. |
|  | Strongly Agree | Agree | Neutral | Disagree | Strongly Disagree |
| 7. The event better prepared me to do my job or perform my role. |
|  | Strongly Agree | Agree | Neutral | Disagree | Strongly Disagree |
| 8. The program incorporated useful lectures and discussion. |
|  | Strongly Agree | Agree | Neutral | Disagree | Strongly Disagree |
| 9. How did you hear about the program today: (circle all that apply) |
|  | APA California’s online calendar | APA California email blast | APA California website | Friend | Other: |
| 10. Why did you choose to attend this event? (circle all that apply) |
|  | Topic | Presenter/Speaker | CM credit | Recommended | Other: |
| What did you like about the program? (circle all that apply) |
|  | Educational | Entertaining | Speaker/Presenter | Topic | Price | Other: |
| 12. Was the presentation easy to see, hear, and understand? |
|  | Yes | No |
| 13. Would you recommend to a friend? |
|  | Yes | No |
| 13. I would like to see future professional development workshops on these subjects: |
| 15. Do you have additional comments or suggestions? |

# Comments

These need to be completed to finalize the book.

This is an area that has not been followed in relation to the budget line items, the registration form and WebRegPro’s fee breakdown setup.  See Appendix L attachment.

If due to attendance size and hotel costs conferences may not be able to held in each Section.  If so should profit distribution addresses this or will Host Sections not be related to the actual location of the Conference?

There should probably be better definition of this.  The best approach would be losses shared according to the profit percentage in section F. above.

Is this in conflict with $100 speaker attendee fee?

Add a section about making someone the point of contact for disability inquiries and complaints concerning the Conference and Conference facilities

Best to provide Board meeting dates for proposing and approving the theme.

Provide a date to assure the program can be approved in time for distribution/printing/ etc.

Its unclear if this is the section or chapter conference program committees?

Isn’t this outdated?

I would assume we want a minimum half-page

Do you mean “ notice/articles’ and not ‘ads’?  If so my prior

Not sure the dates.  I the general/typical months of early and final registration and release could be noted in hear that would be good.

Best to provide general/typical months for these emails.

The CalTrans contract requires 5 transportation related sessions.

Get powerpoints from Tom

Add ADA requirements

Note: This needs updating

.  (See Appendix L)

Should be updated with each conference fee structure.

Please see attached example for the 2009 conference that was recommended/requested but not adopted by conference coordinator/committee.  This would make financial reconciliation more efficient.

The need for seed money from the State is no longer needed as the State maintains the conference checking account which has a beginning balance of $15,000.